## Sheet1
Sprint Planning Capacity Tool
| Base Hours Sprint | Admin Time | Vac/PTO | Holiday | Training | Capacity
Developer 1 | 80 | 8 | 20 | 8 | 4 | 40
Developer 2 | 80 | 8 | 8 | 8 | 4 | 52
Developer 3 | 80 | 8 | 0 | 8 | 2 | 62
Developer 4 | 80 | 8 | 0 | 8 | 0 | 64
Developer 5 | 80 | 8 | 0 | 8 | 0 | 64
Developer 6 | 80 | 8 | 4 | 8 | 0 | 60
Developer 7 | 80 | 8 | 0 | 8 | 0 | 64
Developer 8 | 80 | 8 | 0 | 8 | 0 | 64
Developer 9 | 40 | 4 | 2 | 8 | 0 | 26
Developer 10 | 40 | 4 | 0 | 8 | 0 | 28

## Sheet2
Sprint Planning Capacity Tool
| Base Hours Sprint | Admin Time/Buffer | Vac/PTO | Public Holiday | Training | Capacity
Developer 1 | 80 | 8 | 8 | 0 | 4 | 60
Developer 2 | 80 | 8 | 24 | 0 | 4 | 44
Developer 3 | 80 | 8 | 16 | 0 | 0 | 56
Developer 4 | 80 | 8 | 0 | 0 | 0 | 72
Developer 5 | 80 | 8 | 0 | 0 | 0 | 72
Developer 6 | 80 | 8 | 0 | 0 | 0 | 72
Developer 7 | 80 | 8 | 6 | 0 | 4 | 62
Developer 8 | 80 | 8 | 0 | 0 | 0 | 72
Developer 9 (borrowed resource) | 40 | 4 | 0 | 0 | 0 | 36
Developer 10 (borrowerd resource) | 40 | 4 | 4 | 0 | 0 | 32
Hi Team, |  | Admin time = 10% of base hour
Our next sprint is from 03/22 to 04/04, do you have anything set up during this time? Like Dr Appt, Vac/PTO, Training , AND IF TRAINING how many hours
Thanks

## Actaul capacity
1 STORYPOINT = 2 HOURS
Developers | 100% Capacity for sprint | Actual Capacity ( 80%) | COMMITED STORY POINT
Developer 1 | 60 | 48 | 24
Developer 2 | 44 | 35.2 | 17.6
Developer 3 | 56 | 44.8 | 22.4
Developer 4 | 72 | 57.6 | 28.8
Developer 5 | 72 | 57.6 | 28.8
Developer 6 | 72 | 57.6 | 28.8
Developer 7 | 62 | 49.6 | 24.8
Developer 8 | 72 | 57.6 | 28.8
Developer 9 (borrowed resource) | 36 | 28.8 | 14.4
Developer 10 (borrowerd resource) | 32 | 25.6 | 12.8